## 工作表1
ID | Name | Creation Date | Description | Sprint | Priority | Status | Notes
US1 | Menu | 01/24/2023 | As a user, I hope to have a menu button that allows users to switch UI from one to another so that I can freely choose which category of garbage I want to know/search for. | 1 | High | Done | Renewed in Sprint 2
US2 | App reliability | 01/24/2023 | As a user, I want the app's reliability to be over 90% of successful running. This App would not be interrupted by other apps when it's working and it's compatible with different browsers. | 1 | Medium | Done
US3 | Setup Language | 01/24/2023 | As a user, I want the app's ability to set up the language( Chinese, English, and so on). So I can use it no matter what language I'm using. | 1 | Low | Done
US4 | Welcome Screen | 2023-10-03 | As a user, I want to have an interface that shows me the app's icon when I open the app. | 2 | Low | Done
US5 | Language Switch | 01/24/2023 | As a user, the content of the app should not be confused by the language, I want to set a language change option so that people from a different country can use this app directly. | 1 | Low | Done
US6 | Warning Message | 2023-10-03 | As a user, I want to be warned when performing operations such as reset, so that I never lose my data. | 2 | Medium | Not Done
US7 | Account | 2023-10-03 | As a user, I want my Settings and information to be recorded so that I can respond to my preferences more quickly when changing devices. | 2 | Medium | Done
US8 | Photograph | 01/24/2023 | As a user I would like to have a photo feature within the app so that I can retrieve more content | 1 | High | Done
US9 | Picture Viewer | 01/24/2023 | As a user, I want images to distinguish the types of junk I'm looking for so I don't have to read a lot of text while searching for information. | 1 | High | Done
US10 | Word description | 01/24/2023 | As a user, I need as detailed text description as possible to introduce the knowledge of garbage classification to me, so that as to improve my garbage classification ability. | 1 | Medium | Done
US11 | Help Button | 2023-10-03 | As a user, I want to be able to use the help page when I don't understand a feature in the app so that I can get help where I need it. | 2 | Medium | Not Done
US12 | About | 01/24/2023 | As a user, I would like to know the version of this app, which helps me to update this app in time. | 1 | Low | Done
US13 | UI | 01/24/2023 | As a user, I want the app to have a good UI design, so that I can use it more smoothly | 1 | Large | Done | Renewed in Sprint 2
US14 | Upload picture | 01/24/2023 | As a user, I want to upload the picture I would like to use for my profile. | 1 | Medium | Done
US15 | Settings | 01/24/2023 | As a user, I want to be able to change settings so that I can use the app with my preffered options. | 1 | Medium | Done
US16 | Register | 2023-10-03 | As a user, before I have a account, I want to have a nickname and save my personal imformation on the app, so that I won't reveal my real name, and I won't be asked to re-enter my information when I switch devices. | 2 | High | Done
US17 | Searcher | 01/24/2023 | As a user, I want to search for this item to find out what category it belongs to, so that I can realize how to recycle or dispose of it. | 1 | High | Done
US18 | Text editor | 2023-10-03 | As a user I wish I could search by editing text | 2 | High | Done
US19 | Password Change Function | 2023-10-03 | As a user, I don't want my current password anymore, so that I can click a button to enter a new one. | 2 | High | Done
US20 | Exit Screen | 2023-10-03 | As a user, I want to see a "goodbye, see you next time" sentence when I close the app | 2 | Medium | Done
US21 | Clickable picture | 01/24/2023 | As a user, I want to have a clickable picture so that I can select the detailed spam classification information THAT I want to know/search for. | 1 | Medium | Done | Renewed in Sprint 2
US22 | Logout Function | 2023-10-03 | As a user, I want to have logout function so that I can switch to another account. | 2 | Low | Done
US23 | Records | 2023-10-03 | As a user, I need to create my own trash notepad so that I can keep track of my own trash disposal practices. | 2 | High | Done